## Process_Flow
Business Development
Program
Configuration
Engineering
SCM / Procurement
Tooling
PPC
Production
Quality
Stores

## Q & A
# | Query CIO | Response_MASPL
1 | Business meaning of TRS, TRF and TL Code; and which of Tool Number or TL Code keys a Tool | TRS - Tool Requirement Sheet, TRF - Tool Request Form, TL code - Unique tool code; Tool number is reference, TL code is generated / Keyed in SAP
2 | Meaning of MASPL Level, Type, Safety Class, Process — and whether Safety Class alters which milestones apply | MASPL level, type, safety class, process - these are project based inputs does not alter the milestones
3 | Exact column split between Configuration and Engineering (proposal in §5) | We discussed, Configuration takes input from Engineering and creates WO number for each part number
4 | Whether Engineering's tool columns are dropped and read through from Tooling (proposal in §5) | Yes, part number wise complete data set is pulled in from tooling tracker, need to check on commonlising / automate to unite
5 | Stage closure: self-closure by the owning role in Phase 1, with RFA multi-level approval in Phase 2? | To be discussed
6 | Bid lifecycle — retention of lost and expired bids, superseding vs retaining rounds | Discussed
7 | Who may view RC / NRC / NRC OT prices. The BRD role matrix is silent, which currently exposes pricing to every role | currently this is manual input and saved in SAP
8 | Tool KPI counting under many-to-many — distinct Tools vs Tool Applications | discussed, tool number and part number are many to many relation
9 | Ingestion failure handling — field-level quarantine vs row rejection | To be discussed
10 | Audit identity and source value for machine writes | To be discussed
11 | Whether field ownership is fixed in code or admin-configurable | admin - configurable
12 | Terminal events closing the Tooling and SCM tracks, and whether a part may reach Quality with Tooling open | Final Quality will receive once all the previous gates are closed
13 | What determines that a part has a Tooling track, given the TOOLS NEEDED? flag is unreliable | Concurrent engineering / CFT (Cross functional team ) meeting is conducted and tracked, in engineering tracker Tool Yes or no is a checkpoint
14 | Resolution of SAP STATUS, PRIORITY / ACTION STATUS vocabularies, and WORK CATEGORY | SAP status - daily dump from SAP, priority / action status are manual inputs, work category is from SAP status report
15 | Gate numbering — Tooling uses GATE 1–4, Engineering Dashboard uses GATE 1–8, Tooling Dashboard uses a third set | Yes, Tooling has 4 gates, Engineering as 8 gates, Tooling (TL code generation) is a sub sheet
16 | Archival and retention policy for closed projects and historical WIP | To be discussed on archival and retention policy as per Aero standards
17 | Expected data volume and concurrency for sizing | DATA Volume - we had discussed, currently we are seeing around 10,000 unique part numbers, but the rate at which MASPL is growing we can easily reach around 40 - 50K including continuous deliverables (historic data), live data can be around 20 - 25 K on higher side

## INPUT_BD
| SAP | SAP |  | SAP | SAP | SUPPLIER PORTAL / EMAIL | SUPPLIER PORTAL / EMAIL | MANUAL | MANUAL | FORMULA | FORMULA |  | SAP | SAP | Manual
Doc_type | Doc_No | Doc_Date | sl_no | Version no | Customer_code | Project_Name | Customer_material_code | Price_Currency | RC Price (Basic Price) | NRC Price (Amortisation Price) | NRC Amortised QTY | NRC_OT Price | Bid- Valid_From_date | Bid -Valid_To_date | Planned Submission Date
BID | MASPL-RFQ-ABS-301-2024 | 29.04.2025 | 1 | Round 1 | MSAXYZ0005 | ABS | Z579-13034-304-00 | USD | 1.11 |  |  | 15 | 29.04.2025 | 31.12.2030 | 2024-09-20
BID | MASPL-RFQ-ABS-301-2024 | 29.04.2025 | 2 | Round 1 | MSAXYZ0005 | ABS | Z579-13033-304-00 | USD | 1.12 |  |  | 15 | 29.04.2025 | 31.12.2030 | 2024-09-20
BID | MASPL-RFQ-ABS-301-2024 | 29.04.2025 | 3 | Round 1 | MSAXYZ0005 | ABS | Z579-13037-304-00 | USD | 1.13 |  |  | 15 | 29.04.2025 | 31.12.2030 | 2024-09-20
BID | MASPL-RFQ-ABS-301-2024 | 29.04.2025 | 4 | Round 1 | MSAXYZ0005 | ABS | Z579-13035-304-00 | USD | 1.14 |  |  | 15 | 29.04.2025 | 31.12.2030 | 2024-09-20
BID | MASPL-RFQ-ABS-301-2024 | 29.04.2025 | 5 | Round 1 | MSAXYZ0005 | ABS | Z579-13197-303-00 | USD | 1.15 |  |  | 15 | 29.04.2025 | 31.12.2030 | 2024-09-20
BID | MASPL-RFQ-ABS-301-2024 | 29.04.2025 | 6 | Round 1 | MSAXYZ0005 | ABS | Z579-13031-304-00 | USD | 1.16 |  |  | 15 | 29.04.2025 | 31.12.2030 | 2024-09-20
BID | MASPL-RFQ-ABS-301-2024 | 29.04.2025 | 7 | Round 1 | MSAXYZ0005 | ABS | Z539-10640-000-00 | USD | 1.17 |  |  | 15 | 29.04.2025 | 31.12.2030 | 2024-09-20
BID | MASPL-RFQ-ABS-301-2024 | 29.04.2025 | 8 | Round 1 | MSAXYZ0005 | ABS | X539-36801-303-00 | USD | 1.18 |  |  | 15 | 29.04.2025 | 31.12.2030 | 2024-09-20
BID | MASPL-RFQ-ABS-301-2024 | 29.04.2025 | 9 | Round 1 | MSAXYZ0005 | ABS | Z539-10678-300-00 | USD | 1.19 |  |  | 15 | 29.04.2025 | 31.12.2030 | 2024-09-20
BID | MASPL-RFQ-ABS-301-2024 | 29.04.2025 | 10 | Round 1 | MSAXYZ0005 | ABS | Z539-36801-304-00 | USD | 1.2 |  |  | 25 | 29.04.2025 | 31.12.2030 | 2024-09-20
BID | MASPL-RFQ-ABS-301-2024 | 29.04.2025 | 11 | Round 1 | MSAXYZ0005 | ABS | Z539-36801-306-00 | USD | 1.21 |  |  | 40 | 29.04.2025 | 31.12.2030 | 2024-09-20

## Programs
|  | SUPPLIER PORTAL / EMAIL | SUPPLIER PORTAL / EMAIL | Manual |  |  | SUPPLIER PORTAL / EMAIL | CALCULATION | SAP | SUPPLIER PORTAL / EMAIL | SAP / QUALITY TRACKER | Maunal
| Manual | BD | BD | Manual | Manual | Manual | Manual
|  | Column -1 | Column -2 |  |  |  |  | Column - 4 = Column 3 - 64 days |  | Column - 3
Sr. No. | Customer | Project | Material Number | PART DESCRIPTION | Sub project name | TYPE | Order Type | Planned Launch Date | Actual Release Date | Planned Submission Date | Actual Submission Date | Annual Demand
1 | ATLANTIC | ABS | Z5791303430400 | ANGLE | W1 | DETAIL PART | FAI | 2024-07-18 | 2024-06-20 | 2024-09-20 | 2024-09-26
2 | ATLANTIC | ABS | Z5791303330400 | SHIM | W1 | DETAIL PART | FAI | 2024-07-18 | 2024-06-20 | 2024-09-20 | 2024-09-25
3 | ATLANTIC | ABS | Z5791303730400 | SEN ELEMENT BRACKET | W1 | EQP ASSEMBLY. | FAI | 2024-07-18 | 2024-06-20 | 2024-09-20 | 2024-09-26
4 | ATLANTIC | ABS | Z5791303530400 | CLAMP RING | W1 | DETAIL PART | FAI | 2024-07-18 | 2024-06-20 | 2024-09-20 | 2024-09-20
5 | ATLANTIC | ABS | Z5791319730300 | ACT-PROTECTION GRID | W1 | DETAIL PART | FAI | 2024-07-18 | 2024-08-01 | 2024-09-20 | 2024-09-24
6 | ATLANTIC | ABS | Z5791303130400 | SUPPORT | W1 | DETAIL PART | FAI | 2024-07-18 | 2024-06-20 | 2024-09-20 | 2024-09-26
7 | ATLANTIC | ABS | Z5391064000000 | ANGLE | W1 | DETAIL PART | FAI | 2024-07-18 | 2024-06-21 | 2024-09-20 | 2024-09-24
8 | ATLANTIC | ABS | X5393680130300 | BRACKET | W1 | DETAIL PART | FAI | 2024-07-18 | 2024-06-20 | 2024-09-20 | 2024-09-25
9 | ATLANTIC | ABS | Z5391067830000 | BRACKET F ELECTRIC | W1 | ASSEMBLY | FAI | 2024-07-18 | 2024-06-21 | 2024-09-20 | 2024-09-19
10 | ATLANTIC | ABS | Z5393680130400 | BRACKET F.ELECTRIC | W1 | DETAIL PART | FAI | 2024-07-18 | 2024-08-01 | 2024-09-20 | 2024-09-25
11 | ATLANTIC | ABS | Z5393680130600 | ANGLE | W1 | DETAIL PART | FAI | 2024-07-18 | 2024-08-01 | 2024-09-20 | 2024-09-25
Dropdown value
FAI / DFAI

## Engineering
|  | From SAP | [8 empty] | TDP available or not if available then only insert date | TDP available or not if available then only insert date | [20 empty] | Formula if this part is available in tooling then yes otherwise No | [29 empty] | if inhouse filled by enginnering if outsource then data coming from SCM
[10 empty] | col 13 = col8 - 180 days |  |  | col 12 = col8 - 150 days | [9 empty] | Engineering | Engineering |  |  | col 12 = col8 -120 | [8 empty] | col 11 = col 8 - 21 days | [12 empty] | col 10 = col 7 - 21 days |  |  |  |  | col 9 = col 8 - 7 days |  |  |  | col 8 = col 7 - 4 | [8 empty] | col 7 = col 6- 15 days | SAP | col 6 = col 5 - 7 days | SAP | col 5 = col 4 - 15days | SAP | col 4 = col 3 - 7 days | SAP | col3 =col2 -10 days | SAP | col2 =col1 -3 days | Eng | SAP | SAP | SAP | Eng | Refer - Input Programs - Column 4 COLUMN 1 | SAP | SAP | SAP | SAP | Eng
| manual entery by Eng | BD / Programs | just add - in MASPL | BD / Programs | BD / Programs | BD / Programs | BD / Programs | Engineering | Engineering |  | Engineering | Engineering |  | Engineering | Engineering | Engineering | Engineering | Engineering | Engineering | Engineering | Engineering | Engineering | YES/NO | APPROVED/ME WIP/CUST.WIP | Engineering | Engineering |  | Engineering | Engineering | Engineering | Engineering | Engineering | Engineering | if tool is available then coming from Tooling | [11 empty] | Engineering | Engineering | Engineering |  | Engineering | Engineering | Engineering | Engineering |  | Engineering | SAP | SAP | Configuration | Engineering | Configuration | Engineering | Engineering | Engineering | Engineering | Engineering | Engineering | 7 |  | 15 |  | 7 |  | 15 |  | 7
[10 empty] | TDP |  |  | FEASIBILITY STUDY |  |  | BOM CREATION |  |  | CUSTOMER APPROVAL | [7 empty] | CONCURRENCE |  |  | TOOL APPROVAL |  |  | TOOLS | [12 empty] | RAW MATERIAL & BOI | [6 empty] | NC PROGRAM STATUS |  |  | FAI LAUNCH STSTUS | [10 empty] | ISSUE OF RM |  | COMP |  | PART CONFIG (FORMING +HT+M/C) |  | SST |  | ASSY |  | FINAL INSPECTION |  |  |  |  | FAI SUBMISSION
Sl.No | MASPL LEVEL | MASPL PN (AS PER SAP) | CUSTOMER PN | PART DESCRIPTION | Project | Sub project name | TYPE | SAFETY CLASS | PROCESS | TDP PLAN DATE | TDP ACTUAL DATE | TDP AVAILABILITY | FEASIBILITY PLAN DATE | FEASIBILITY ACTUAL DATE | FEASIBILTY STUDY | RM BOM STATUS | CONSUMABLE BOM STATUS | HW BOM STATUS | SST PROCESS QUALIFICATION REQUIREMENTS | SST PROCESS NEEDED QULIFICATION | SST PROCESS QUALIFICATION STATUS | LAI APPROVAL | FPQ APPROVAL REQUIREMENTS | FPQ APPROVAL STATUS | ME EDC | CUST. EDC | CONCURRENCE PLAN DATE | CONCURRENCE ACTUAL DATE | CONCURRENCE STATUS | TOOL CONCEPT REQUIREMENTS | TOOL CONCEPT APPROVAL STATUS | TOOL DESIGN APPROVAL | TOOLS NEEDED? | TOOL TYPE | NO OF TOOLS | TOOL PLAN DATE | COMMITTED DATE | TOOL ACTUAL DATE | TOOL AVAILIABILITY | TRF HANDOVER | TOOL DESIGN | TOOL FABRICATION | TOOL NUMBER | TL CODE | DEPENDENCY | FINAL TEMP | THICKNESS | RM/BOI Num (as per SAP) | RM NEED DATE | BOI NEED DATE | RM STATUS | BOI STATUS | NC PROGRAM TYPE | NC PROGRAM COMPLETION PLAN DATE | NC PROGRAM COMPLETION ACTUAL DATE | W/O - SAP | W/O Date - SAP | WO PLAN RELEASE DATE | DELINQUENCY | LAUNCH STATUS | LC DEPENDENCY | LC DEPENDENCY BREAKUP | DOSSIAR INHOUSE/OUTSOURCE | PRIORITY | TQ REQUIRED | TQ RAISED | PLAN DATE | ACTUAL DATE | PLAN DATE | ACTUAL DATE | PLAN DATE | ACTUAL DATE | PLAN DATE | ACTUAL DATE | PLAN DATE | ACTUAL DATE | PLAN DATE | Revised Plan | Comp. FI & SST | Comp. FI & LC | ACTUAL DATE | REVIEW | FAI SUBMISSION PLAN DATE | FAI SUBMISSION ACTUAL DATE | DELAY | FAI SUBMISSION DEPENDENCY | FAI SUBMISSION DEPENDENCY BREAKUP | Remarks
13 |  | Z5791303430400 | Z579-13034-304-00 | ANGLE | ABS | W1 | DETAIL PART |  | ROUTING+PB | 2023-10-13 | 2023-10-13 | TDP AVAILABLE | 2023-11-12 | 2023-11-12 | FEASIBILITY STUDY COMPLETED | COMPLETED | COMPLETED | COMPLETED | NO | NA | NA | [5 empty] | 2023-12-12 | 2023-12-12 | CONCURRENCE COMPLETED |  |  |  | NO | NA | NA | NA | NA | NA | NA |  | NA | NA |  |  | NA | T351 | 1.2 |  | 2024-03-24 |  |  |  |  | 2024-04-05 |  | 21002672 | 2024-03-11 | 2024-04-10 |  | LAUNCHED | NA | NA | NA | NA | NO | NO | 2024-04-14 | 2024-04-04 | 2024-04-19 |  | 2024-04-23 |  | 2024-05-08 |  |  |  | 2024-09-17 | [5 empty] | 2024-09-20 | 2024-09-26 |  |  | FAI SUBMITTED
14 |  | Z5791303330400 | Z579-13033-304-00 | SHIM | ABS | W1 | DETAIL PART |  | ROUTING | 2023-10-13 | 2023-10-13 | TDP AVAILABLE | 2023-11-12 | 2023-11-12 | FEASIBILITY STUDY COMPLETED | COMPLETED | COMPLETED | COMPLETED | NO | NA | NA | [5 empty] | 2023-12-12 | 2023-12-12 | CONCURRENCE COMPLETED |  |  |  | NO | NA | NA | NA | NA | NA | NA |  | NA | NA |  |  | NA | T351 | 1.2 |  | 2024-03-24 |  |  |  |  | 2024-04-05 |  | 21002756 | 2024-03-15 | 2024-04-10 |  | LAUNCHED | NA | NA | NA | NA | NO | NO | 2024-04-14 | 2024-04-04 | 2024-04-19 |  | 2024-04-23 |  | 2024-05-08 |  |  |  | 2024-09-17 | [5 empty] | 2024-09-20 | 2024-09-25 |  |  | FAI SUBMITTED
15 |  | Z5791303730400 | Z579-13037-304-00 | SEN ELEMENT BRACKET | ABS | W1 | EQP ASSEMBLY. |  |  | 2025-04-24 | 2025-04-24 | TDP AVAILABLE | 2025-05-24 | 2025-05-24 | FEASIBILITY STUDY COMPLETED | COMPLETED | COMPLETED | COMPLETED | NO | NA | NA | [5 empty] | 2025-06-23 | 2025-06-23 | CONCURRENCE COMPLETED |  |  |  | NO | NA | NA | NA | NA | NA | NA |  | NA | NA |  |  | NA | 1.4544.9 | 0.6 |  | 2025-10-04 |  |  |  |  | 2025-10-16 |  | 21014016 | 2025-11-18 | 2025-10-21 |  | LAUNCHED | NA | NA | NA | NA | NO | NO | 2025-10-25 | 2025-10-25 | 2025-10-30 |  | 2025-11-03 |  | 2025-11-18 |  |  |  | 2024-09-17 | [5 empty] | 2024-09-20 | 2024-09-26 |  |  | FAI SUBMITTED
16 |  | Z5791303530400 | Z579-13035-304-00 | CLAMP RING | ABS | W1 | DETAIL PART |  | LASER+HEZ+PRESS | 2025-01-22 | 2025-01-22 | TDP AVAILABLE | 2025-02-21 | 2025-02-21 | FEASIBILITY STUDY COMPLETED | COMPLETED | COMPLETED | COMPLETED | NO | NA | NA | [5 empty] | 2025-03-23 | 2025-03-23 | CONCURRENCE COMPLETED |  |  |  | YES | PRESS TOOL |  |  |  | 2024-07-01 | YES | YES | COMPLETED | COMPLETED |  | TL0340080010003 | NA | 1.4544.9 | 2 |  | 2025-07-04 |  |  |  |  | 2025-07-16 |  | 21011803 | 2025-07-18 | 2025-07-21 |  | LAUNCHED | NA | NA | NA | NA | NO | NO | 2025-07-25 | 2025-07-25 | 2025-07-30 |  | 2025-08-03 |  | 2025-08-18 |  |  |  | 2024-09-17 | [5 empty] | 2024-09-20 | 2024-09-20 |  |  | FAI SUBMITTED
17 |  | Z5791319730300 | Z579-13197-303-00 | ACT-PROTECTION GRID | ABS | W1 | DETAIL PART |  | ROUTING+PB | 2024-01-18 | 2024-01-18 | TDP AVAILABLE | 2024-02-17 | 2024-02-17 | FEASIBILITY STUDY COMPLETED | COMPLETED | COMPLETED | COMPLETED | NO | NA | NA | [5 empty] | 2024-03-18 | 2024-03-18 | CONCURRENCE COMPLETED |  |  |  | NO | NA | NA | NA | NA | NA | NA |  | NA | NA |  |  | NA | T42 | 1.2 |  | 2024-06-29 |  |  |  |  | 2024-07-11 |  | 21005043 | 2024-07-18 | 2024-07-16 |  | LAUNCHED | NA | NA | NA | NA | NO | NO | 2024-07-20 | 2024-07-18 | 2024-07-25 |  | 2024-07-29 |  | 2024-08-13 |  |  |  | 2024-09-17 | [5 empty] | 2024-09-20 | 2024-09-24 |  |  | FAI SUBMITTED
18 |  | Z5791303130400 | Z579-13031-304-00 | SUPPORT | ABS | W1 | DETAIL PART |  | ROUTING+PB | 2023-10-08 | 2023-10-08 | TDP AVAILABLE | 2023-11-07 | 2023-11-07 | FEASIBILITY STUDY COMPLETED | COMPLETED | COMPLETED | COMPLETED | NO | NA | NA | [5 empty] | 2023-12-07 | 2023-12-07 | CONCURRENCE COMPLETED |  |  |  | NO | NA | NA | NA | NA | NA | NA |  | NA | NA |  |  | NA | T42 | 1.6 |  | 2024-03-19 |  |  |  |  | 2024-03-31 |  | 21003087 | 2024-04-05 | 2024-04-05 |  | LAUNCHED | NA | NA | NA | NA | NO | NO | 2024-04-09 | 2024-04-04 | 2024-04-14 |  | 2024-04-18 |  | 2024-05-03 |  |  |  | 2024-09-17 | [5 empty] | 2024-09-20 | 2024-09-26 |  |  | FAI SUBMITTED
19 |  | Z5391064000000 | Z539-10640-000-00 | ANGLE | ABS | W1 | DETAIL PART |  | ROUTING+PB | 2024-08-24 | 2024-08-24 | TDP AVAILABLE | 2024-09-23 | 2024-09-23 | FEASIBILITY STUDY COMPLETED | COMPLETED | COMPLETED | COMPLETED | NO | NA | NA | [5 empty] | 2024-10-23 | 2024-10-23 | CONCURRENCE COMPLETED |  |  |  | NO | NA | NA | NA | NA | NA | NA |  | NA | NA |  |  | NA | T42 | 1.6 |  | 2025-02-03 |  |  |  |  | 2025-02-15 |  | 21007077 | 2025-02-07 | 2025-02-20 |  | LAUNCHED | NA | NA | NA | NA | NO | NO | 2025-02-24 | 2025-02-24 | 2025-03-01 |  | 2025-03-05 |  | 2025-03-20 |  |  |  | 2024-09-17 | [5 empty] | 2024-09-20 | 2024-09-24 |  |  | FAI SUBMITTED
20 |  | X5393680130300 | X539-36801-303-00 | BRACKET | ABS | W1 | DETAIL PART |  | ROUTING+PB+HF | 2024-10-11 | 2024-10-11 | TDP AVAILABLE | 2024-11-10 | 2024-11-10 | FEASIBILITY STUDY COMPLETED | COMPLETED | COMPLETED | COMPLETED | NO | NA | NA | [5 empty] | 2024-12-10 | 2024-12-10 | CONCURRENCE COMPLETED |  |  |  | YES | HAND FORMING TOOL |  |  |  |  | YES | YES | COMPLETED | COMPLETED |  |  | NA | T42 | 1.2 |  | 2025-03-23 |  |  |  |  | 2025-04-04 |  | 21009445 | 2025-03-24 | 2025-04-09 |  | LAUNCHED | NA | NA | NA | NA | NO | NO | 2025-04-13 | 2025-04-13 | 2025-04-18 |  | 2025-04-22 |  | 2025-05-07 |  |  |  | 2024-09-17 | [5 empty] | 2024-09-20 | 2024-09-25 |  |  | FAI SUBMITTED
21 |  | Z5391067830000 | Z539-10678-300-00 | BRACKET F ELECTRIC | ABS | W1 | ASSEMBLY |  |  | 2023-11-13 | 2023-11-13 | TDP AVAILABLE | 2023-12-13 | 2023-12-13 | FEASIBILITY STUDY COMPLETED | COMPLETED | COMPLETED | COMPLETED | NO | NA | NA | [5 empty] | 2024-01-12 | 2024-01-12 | CONCURRENCE COMPLETED |  |  |  | NO | NA | NA | NA | NA | NA | NA |  | NA | NA |  |  | NA | T351 | 1 |  | 2024-04-24 |  |  |  |  | 2024-05-06 |  | 21003861 | 2024-05-15 | 2024-05-11 |  | LAUNCHED | NA | NA | NA | NA | NO | NO | 2024-05-15 | 2024-05-10 | 2024-05-20 |  | 2024-05-24 |  | 2024-06-08 |  |  |  | 2024-09-17 | [5 empty] | 2024-09-20 | 2024-09-19 |  |  | FAI SUBMITTED
22 |  | Z5393680130400 | Z539-36801-304-00 | BRACKET F.ELECTRIC | ABS | W1 | DETAIL PART |  | ROUTING+PB | 2023-07-01 | 2023-07-01 | TDP AVAILABLE | 2023-07-31 | 2023-07-31 | FEASIBILITY STUDY COMPLETED | COMPLETED | COMPLETED | COMPLETED | NO | NA | NA | [5 empty] | 2023-08-30 | 2023-08-30 | CONCURRENCE COMPLETED |  |  |  | NO | NA | NA | NA | NA | NA | NA |  | NA | NA |  |  | NA | T42 | 1.2 |  | 2023-12-11 |  |  |  |  | 2023-12-23 |  | 21001863 | 2024-01-25 | 2023-12-28 |  | LAUNCHED | NA | NA | NA | NA | NO | NO | 2024-01-01 | 2023-12-27 | 2024-01-06 |  | 2024-01-10 |  | 2024-01-25 |  |  |  | 2024-09-17 | [5 empty] | 2024-09-20 | 2024-09-25 |  |  | FAI SUBMITTED
23 |  | Z5393680130600 | Z539-36801-306-00 | ANGLE | ABS | W1 | DETAIL PART |  | ROUTING+CHAMFER+PB | 2023-09-08 | 2023-09-08 | TDP AVAILABLE | 2023-10-08 | 2023-10-08 | FEASIBILITY STUDY COMPLETED | COMPLETED | COMPLETED | COMPLETED | NO | NA | NA | [5 empty] | 2023-11-07 | 2023-11-07 | CONCURRENCE COMPLETED |  |  |  | NO | NA | NA | NA | NA | NA | NA |  | NA | NA |  |  | NA | T762 | 2.5 |  | 2024-02-18 |  |  |  |  | 2024-03-01 |  | 21003799 | 2024-05-15 | 2024-03-06 |  | LAUNCHED | NA | NA | NA | NA | NO | NO | 2024-03-10 | 2024-03-10 | 2024-03-15 |  | 2024-03-19 |  | 2024-04-03 |  |  |  | 2024-09-17 | [5 empty] | 2024-09-20 | 2024-09-25 |  |  | FAI SUBMITTED
Formulas:
col 13 = col8 - 180 days = [col 8 = col 7 - 4]-180
col 12 = col8 - 150 days = [col 8 = col 7 - 4]-150
col 12 = col8 -120 = [col 8 = col 7 - 4]-120
col 10 = col 7 - 21 days = [col 7 = col 6- 15 days]-21
col 9 = col 8 - 7 days = [col 8 = col 7 - 4]-5
col 8 = col 7 - 4 = [col 7 = col 6- 15 days]-4
col 6 = col 5 - 7 days = [col 7 = col 6- 15 days]+5
col 5 = col 4 - 15days = [col 6 = col 5 - 7 days]+4
col 4 = col 3 - 7 days = [col 5 = col 4 - 15days]+15
col2 =col1 -3 days = [FAI SUBMISSION PLAN DATE]-3

## Tooling
| MASTER TRACKER | MASTER TRACKER | MASTER TRACKER | MANUAL | FORMULA / MASTER TRACKER | BD / PROGRAMS | MASTER TRACKER | FORMULA | MANUAL | MANUAL | FORMULA | MANUAL | MANUAL | TOOLING SUB - TRACKER | MANUAL | MANUAL | MANUAL | MANUAL | MANUAL | FORMULA | MANUAL | MANUAL | MANUAL | FROM SCM TRACKER | FROM SCM TRACKER | FROM SCM TRACKER | FORMULA | FORMULA | MANUAL | MANUAL | MANUAL | MANUAL | MANUAL | MANUAL | MANUAL | DROP DOWN | FORMULA | MANUAL | MANUAL | MANUAL | MANUAL | TOOLING SUB TRACKER | DROP DOWN | MANUAL | FORMULA | MANUAL | MANUAL | MANUAL | FROM SCM TRACKER | FROM SCM TRACKER | FROM SCM TRACKER | FORMULA | FORMULA | FROM SCM TRACKER | FROM SCM TRACKER | MANUAL | FORMULA | MANUAL | MANUAL | MANUAL | MANUAL | MANUAL | MANUAL | MANUAL | MANUAL | MANUAL | MANUAL | MANUAL | FORMULA | MANUAL
[7 empty] | Column 1 = column 4 from Programs | column 2 = column 1 -21 |  |  | col 8 = col 7 - 22 | [15 empty] | col 7 = col 6 -60 | col 6= col5 -15 | [16 empty] | col 5 = col 4 - 7 | [6 empty] | Col 4 = col 3 - 90 | Column 3 = col 2 -21 days
[9 empty] | GATE-1 | [9 empty] | SCM | [11 empty] | CustomerApproval |  |  | GATE-2 | [9 empty] | SCM | [14 empty] | YES / NO | GATE-3 |  | GATE-4
SL.No | Customer | Project | Derivable Part No | Part No | SAP No | Annual Demand | Part Launch Date | Tool Lob Date | C.E Input Data validation | Remarks(C.E) | TRF Plan Date | TRF Act Date | TRF No | Tool Number | Tool Description | Operation | Complexity | Design (Inhouse¦Outsourced ) | TRS Number(Design) | TRS Plan Date(Design) | TRS Act Date (Design) | PR Number (Design) | PR Date (Design) | PO Date(Design) | PO No(Design) | Vendor Info (Design) | Design Start Date (Plan) | Design End Date (Plan) | Design Start Date (Actual) | Design End Date (Actual) | Applicability | Cust. Plan Date | Cust. Actual Date | MASPL Tool Design Validation | Validation Remarks | Design Status | Delay (Design) | Delay Reason (Design) | Tool Length | Tool Width | Tool Height | TL CODE (SAP) | Manufacturing (Outsourced ) | TRS (Mfg) | TRS Plan Date(Mfg) | TRS Act Date (Mfg) | PR Number(Mfg) | PR Date (Mfg) | PO Date (Mfg) | PO No (Mfg) | Vendor Info (Mfg) | Mfg Start Date (Plan) | Mfg End Date (Plan) | Supplier Commited Date | Tool Received Date | Mfg Status | Delay (Mfg) | Delay Reason (Mfg) | MASPL Tooling Quality Acceptance | MASPL Tool Buy-Off (Mfg) | Buy-Off Remarks(Mfg) | FAI TOOL PROVEOUT | Proveout Remarks | ACCEPTANCE / REJECTION CRITERIA | Tool Handover to Stores | TOOL LIFE CYCLE | Validation Frequency | Previous Validation Date | Next Validation Date | Remarks
1 | ATLANTIC | ABS | Z5791303430400 | Z579-13034-304-00 | Z5791303430400 |  | 2024-07-18 | 2024-06-27 | Yes |  | 2023-12-16 |  |  | 48500D57914677200000 | MILLING FIXTURE | CNC Machining | Medium | IN-HOUSE | N/A | [7 empty] | 2024-01-07 | 2024-03-07 | 2024-12-18 | 2024-12-20 | No |  |  | Yes |  | Completed | #REF! |  | 330 | 192 | 103 | TL0360090010001 | OUTSOURCE | TRS-1762 | 2024-03-22 | 2024-12-20 | 1128571993 | 2024-12-20 | #REF! | #REF! | #REF! | 2024-03-29 | 2024-06-27 | #REF! | 2024-07-12 | Received from Vendor | #REF! | [9 empty] | 1 year | 2024-07-12 | 2025-07-12
2 | ATLANTIC | ABS | Z5791303330400 | Z579-13033-304-00 | Z5791303330400 |  | 2024-07-18 | 2024-06-27 | Yes |  | 2023-12-16 |  |  | 48500D57914677200000 | MILLING FIXTURE | CNC Machining | Medium | IN-HOUSE | N/A | [7 empty] | 2024-01-07 | 2024-03-07 | 2024-12-18 | 2024-12-20 | No |  |  | Yes |  | Completed | #REF! |  | 330 | 192 | 103 | TL0360090010001 | OUTSOURCE | TRS-1762 | 2024-03-22 | 2024-12-20 | 1128571993 | 2024-12-20 | #REF! | #REF! | #REF! | 2024-03-29 | 2024-06-27 | #REF! | 2024-07-17 | Received from Vendor | #REF! | [9 empty] | 1 year | 2024-07-17 | 2025-07-17
3 | ATLANTIC | ABS | Z5791303730400 | Z579-13037-304-00 | Z5791303730400 |  | 2024-07-18 | 2024-06-27 | Yes |  | 2023-12-16 |  |  | 54100D53931727200000 | PRESS TOOL | Forming | Medium | IN-HOUSE | N/A | [7 empty] | 2024-01-07 | 2024-03-07 | 2024-12-07 | 2024-12-09 | No |  |  | Yes |  | Completed | #REF! |  | 225 | 120 | 71.2 | TL0360080010005 | OUTSOURCE | TRS-1176 | 2024-03-22 | 2024-12-09 | 1128571993 | 2024-09-12 | #REF! | #REF! | #REF! | 2024-03-29 | 2024-06-27 | #REF! | 2024-07-22 | Received from Vendor | #REF! | [9 empty] | 1 year | 2024-07-22 | 2025-07-22
4 | ATLANTIC | ABS | Z5791303530400 | Z579-13035-304-00 | Z5791303530400 |  | 2024-07-18 | 2024-06-27 | Yes |  | 2023-12-16 |  |  | 54100D53922064200000 | FORM BLOCK | Forming | Medium | IN-HOUSE | N/A | [7 empty] | 2024-01-07 | 2024-03-07 | 2024-12-18 | 2024-12-20 | No |  |  | Yes |  | Completed | #REF! |  | 128 | 102 | 82 | TL0360010010003 | OUTSOURCE | TRS-1762 | 2024-03-22 | 2024-12-20 | 1128571993 | 2024-12-20 | #REF! | #REF! | #REF! | 2024-03-29 | 2024-06-27 | #REF! | 2024-06-27 | Received from Vendor | #REF! | [9 empty] | 1 year | 2024-06-27 | 2025-06-27
5 | ATLANTIC | ABS | Z5791319730300 | Z579-13197-303-00 | Z5791319730300 |  | 2024-07-18 | 2024-06-27 | Yes |  | 2023-12-16 |  |  | 54100E53911171204000 | FORM BLOCK | Forming | Medium | IN-HOUSE | N/A | [7 empty] | 2024-01-07 | 2024-03-07 | 2024-12-18 | 2024-12-20 | No |  |  | Yes |  | Completed | #REF! |  | 380 | 369 | 57 | TL0360010010004 | OUTSOURCE | TRS-1762 | 2024-03-22 | 2024-12-20 | 1128571993 | 2024-12-20 | #REF! | #REF! | #REF! | 2024-03-29 | 2024-06-27 | #REF! | 2024-07-05 | Received from Vendor | #REF! | [9 empty] | 1 year | 2024-07-05 | 2025-07-05
6 | ATLANTIC | ABS | Z5791303130400 | Z579-13031-304-00 | Z5791303130400 |  | 2024-07-18 | 2024-06-27 | Yes |  | 2023-12-16 |  |  | 54100A53610044208000 | FORM BLOCK | Forming | Medium | IN-HOUSE | N/A | [7 empty] | 2024-01-07 | 2024-03-07 | 2025-05-10 | 2025-05-12 | No |  |  | Yes |  | Completed | #REF! |  | 130 | 92.9 | 40 | TL0360010010053 | OUTSOURCE | TRS-1854 | 2024-03-22 | 2025-05-12 | 1129153035 | 2025-05-12 | #REF! | #REF! | #REF! | 2024-03-29 | 2024-06-27 | #REF! | 2024-07-23 | Received from Vendor | #REF! | [9 empty] | 1 year | 2024-07-23 | 2025-07-23
7 | ATLANTIC | ABS | Z5391064000000 | Z539-10640-000-00 | Z5391064000000 |  | 2024-07-18 | 2024-06-27 | Yes |  | 2023-12-16 |  |  | 54100A53610044209000 | FORM BLOCK | Forming | Medium | IN-HOUSE | N/A | [7 empty] | 2024-01-07 | 2024-03-07 | 2025-05-10 | 2025-05-12 | No |  |  | Yes |  | Completed | #REF! |  | 130 | 92.9 | 40 | TL0360010010054 | OUTSOURCE | TRS-1854 | 2024-03-22 | 2025-05-12 | 1129153035 | 2025-05-12 | #REF! | #REF! | #REF! | 2024-03-29 | 2024-06-27 | #REF! | 2024-08-01 | Received from Vendor | #REF! | [9 empty] | 1 year | 2024-08-01 | 2025-08-01
8 | ATLANTIC | ABS | X5393680130300 | X539-36801-303-00 | X5393680130300 |  | 2024-07-18 | 2024-06-27 | Yes |  | 2023-12-16 |  |  | 48500A53610221316000 | MILLING FIXTURE | CNC Machining | Simple | IN-HOUSE | N/A | [7 empty] | 2024-01-07 | 2024-03-07 | 2025-06-01 | 2025-06-03 | No |  |  | Yes |  | Completed | #REF! |  | 250 | 110 | 25 | TL0360090010066 | OUTSOURCE | TRS-1875 | 2024-03-22 | 2025-06-03 | 1129250005 | 2025-06-03 | #REF! | #REF! | #REF! | 2024-03-29 | 2024-06-27 | #REF! | 2024-06-30 | Received from Vendor | #REF! | [9 empty] | 1 year | 2024-06-30 | 2025-06-30
9 | ATLANTIC | ABS | Z5391067830000 | Z539-10678-300-00 | Z5391067830000 |  | 2024-07-18 | 2024-06-27 | Yes |  | 2023-12-16 |  |  | 54100D21210684200000 | FORM BLOCK | Forming | Simple | IN-HOUSE | N/A | [7 empty] | 2024-01-07 | 2024-03-07 | 2025-06-15 | 2025-06-17 | No |  |  | Yes |  | Completed | #REF! |  | 200 | 160 | 56.8 | TL0360010010080 | OUTSOURCE | TRS-1895 | 2024-03-22 | 2025-06-17 | 1129377449 | 2025-06-17 | #REF! | #REF! | #REF! | 2024-03-29 | 2024-06-27 | #REF! | 2024-07-07 | Received from Vendor | #REF! | [9 empty] | 1 year | 2024-07-07 | 2025-07-07
10 | ATLANTIC | ABS | Z5393680130400 | Z539-36801-304-00 | Z5393680130400 |  | 2024-07-18 | 2024-06-27 | Yes |  | 2023-12-16 |  |  | 54100D53230653200000 | FORM BLOCK | Forming | Simple | IN-HOUSE | N/A | [7 empty] | 2024-01-07 | 2024-03-07 | 2025-04-07 | 2025-04-09 | No |  |  | Yes |  | Completed | #REF! |  | 195 | 63.1 | 48 | TL0360010010045 | OUTSOURCE | TRS-1833 | 2024-03-22 | 2025-04-09 | 1129025298 | 2025-04-09 | #REF! | #REF! | #REF! | 2024-03-29 | 2024-06-27 | #REF! | 2024-07-06 | Received from Vendor | #REF! | [9 empty] | 1 year | 2024-07-06 | 2025-07-06
11 | ATLANTIC | ABS | Z5393680130600 | Z539-36801-306-00 | Z5393680130600 |  | 2024-07-18 | 2024-06-27 | Yes |  | 2023-12-16 |  |  | 54100D53230654200000 | FORM BLOCK | Forming | Simple | IN-HOUSE | N/A | [7 empty] | 2024-01-07 | 2024-03-07 | 2025-04-07 | 2025-04-09 | No |  |  | Yes |  | Completed | #REF! |  | 165 | 43 | 52 | TL0360010010043 | OUTSOURCE | TRS-1833 | 2024-03-22 | 2025-04-09 | 1129025298 | 2025-04-09 | #REF! | #REF! | #REF! | 2024-03-29 | 2024-06-27 | #REF! | 2024-07-03 | Received from Vendor | #REF! | [9 empty] | 1 year | 2024-07-03 | 2025-07-03
[9 empty] | C.E Input Data validation | [5 empty] | Tool Description |  | Complexity | Sourcing | [15 empty] | MASPL Tool Design Validation |  | Tool Design Status |  | Design Delay | [17 empty] | Manufacturing Status |  | Manufacturing delay |  | MASPL Tool Buy-Off (Mfg) |  | FAI TOOL PROVEOUT
[9 empty] | YES | [5 empty] | DRILL JIG |  | Simple | IN-HOUSE | [15 empty] | YES |  | Completed |  | Requirements not finalized | [17 empty] | Completed (IN-HOUSE) |  | RFQ / quotation delay |  | YES |  | YES
[9 empty] | NO | [5 empty] | CHECKING FIXTURE |  | Medium | OUTSOURCE | [15 empty] | NO |  | Work In Progress |  | Frequent design changes | [17 empty] | Work In Progress at Vendor |  | PO release delay |  | NO |  | NO
[15 empty] | CHECK FIXTURE |  | Complex | CUSTOMER | [17 empty] | Delayed |  | Customer clarification pending | [17 empty] | Delayed by Vendor |  | Vendor capacity constraints
[15 empty] | FORM BLOCK |  | Very Complex | YET TO PLAN | [17 empty] | On Track |  | Input data awaited | [17 empty] | On Track at Supplier |  | Material procurement delay by vendor
[15 empty] | FORM BLOCK-2 | [20 empty] | Under Review |  | Dependency on other teams | [17 empty] | RFQ Sent / Awaiting Quote |  | Supplier manufacturing backlog
[15 empty] | PRESS TOOL | [20 empty] | Pending Approval |  | Review comments not closed | [17 empty] | Under PO Creation |  | Quality issues at vendor
[15 empty] | MILLING FIXTURE | [20 empty] | On Hold |  | Approval delay | [17 empty] | Material Procurement by Vendor |  | Rework at supplier
[15 empty] | HOLDING FIXTURE/MILLING FIXTURE | [20 empty] | Blocked |  | Resource unavailability | [17 empty] | Approval Pending |  | Inspection / approval delay
[15 empty] | INSPECTION TEMPLATE | [20 empty] | Rework Required |  | Tool/spec changes | [17 empty] | Quality Issue at Supplier |  | Dispatch delay from vendor
[15 empty] | SHOP AID | [20 empty] | Cancelled |  | Rework due to errors | [17 empty] | Rework at Vendor |  | Insufficient Data
[15 empty] | HAND FORM BLOCK | [20 empty] | Not Started |  | Customer Data Pack Revised | [17 empty] | Dispatch Pending from Vendor |  | Supplier-side hold
[15 empty] | FORM BLOCK | [20 empty] | Design Shared to Customer | [19 empty] | In Transit |  | Communication delay with vendor
[15 empty] | FORM BLOCK STAGE-2 | [40 empty] | Received from Vendor
[15 empty] | HOLDING FIXTURE | [40 empty] | PO Issue
[15 empty] | BEARING PRESSING TOOL | [40 empty] | Design Not Released For Manufacturing
[15 empty] | PRESS SWAGING TOOL | [40 empty] | Hold
[15 empty] | BEARING LOAD TESTING | [40 empty] | Source Inspection required
BEARING LOAD TESTING TOOL
HAND FORM TOOL
STRECH FORMING TOOL
FORM BLOCK(stage-1)
FORM BLOCK(stage-2)
HAND FORM
STRETCH FORM TOOL
Check Template
HAND FORM BLOCK(1:1)
INSPECTION FIXTURE
Formulas:
MASTER TRACKER = XLOOKUP([MASTER TRACKER],Programs!D:D,Programs!I:I)
FORMULA = IFERROR(([MASTER TRACKER]-21),"")
FORMULA = IFERROR(([FORMULA]-22),"")
MANUAL = IF([FROM SCM TRACKER]="","",[FROM SCM TRACKER])

## SCM
| MASTER TRACKER | TOOLING TRACKER | TOOLING TRACKER | SAP | SAP | TOOLING TRACKER | TOOLING TRACKER |  | MANUAL | SAP | SAP | MANUAL | MANUAL | MANUAL | MANUAL
SI NO | Customer / Department | TRS | PR No. | Item of requisition | PR + Data Sharing date | TL code | Description | QTY | Supplier | PO No. | PO Date | Current Status/ Live Status | First cut ETA | Updated ETA | Remarks
1 | ABS | TRS-1762 | 1128571993 | 10 | 2024-12-20 | TL0360090010001 | MILLING FIXTURE | 1 | Inovit Aerospace Solutions | 12300261382 | 2025-01-04 | Delivered | 2024-06-27 | 2024-07-12
2 | ABS | TRS-1762 | 1128571993 | 20 | 2024-12-20 | TL0360090010001 | MILLING FIXTURE | 1 | Inovit Aerospace Solutions | 12300261382 | 2025-01-04 | Delivered | 2024-06-27 | 2024-07-17
3 | ABS | TRS-1176 | 1128571993 | 10 | 2024-09-12 | TL0360080010005 | PRESS TOOL | 1 | Planetto Tooltech | 12300261538 | 2024-09-27 | Delivered | 2024-06-27 | 2024-07-22
4 | ABS | TRS-1762 | 1128571993 | 20 | 2024-12-20 | TL0360010010003 | FORM BLOCK | 1 | Planetto Tooltech | 12300261538 | 2025-01-04 | Delivered | 2024-06-27 | 2024-06-27
5 | ABS | TRS-1762 | 1128571993 | 30 | 2024-12-20 | TL0360010010004 | FORM BLOCK | 1 | Planetto Tooltech | 12300261538 | 2025-01-04 | Delivered | 2024-06-27 | 2024-07-05
6 | ABS | TRS-1854 | 1129153035 | 40 | 2025-05-12 | TL0360010010053 | FORM BLOCK | 1 | Planetto Tooltech | 12300261538 | 2025-05-27 | Delivered | 2024-06-27 | 2024-07-23
7 | ABS | TRS-1854 | 1129153035 | 50 | 2025-05-12 | TL0360010010054 | FORM BLOCK | 1 | Planetto Tooltech | 12300261538 | 2025-05-27 | Delivered | 2024-06-27 | 2024-08-01
8 | ABS | TRS-1875 | 1129250005 | 60 | 2025-06-03 | TL0360090010066 | MILLING FIXTURE | 1 | Planetto Tooltech | 12300261538 | 2025-06-18 | Delivered | 2024-06-27 | 2024-06-30
9 | ABS | TRS-1895 | 1129377449 | 10 | 2025-06-17 | TL0360010010080 | FORM BLOCK | 1 | Planetto Tooltech | 12300262066 | 2025-07-02 | Delivered | 2024-06-27 | 2024-07-07
10 | ABS | TRS-1833 | 1129025298 | 20 | 2025-04-09 | TL0360010010045 | FORM BLOCK | 1 | Planetto Tooltech | 12300262066 | 2025-04-24 | Delivered | 2024-06-27 | 2024-07-06
11 | ABS | TRS-1833 | 1129025298 | 30 | 2025-04-09 | TL0360010010043 | FORM BLOCK | 1 | Planetto Tooltech | 12300262066 | 2025-04-24 | Delivered | 2024-06-27 | 2024-07-03

## PPC
|  |  | formula = today()- previous operation confirmation date | [9 empty] | SAP routing - last operation | Based SAP routing manual check for assy WC
SAP DATA | SAP DATA | SAP DATA | SAP | MASTER TRACKER | MANUAL UPDATED | SAP | SAP | MANUAL | Manual | Master tracker | MANUAL | MANUAL | PROCESS SHEET | Manual | Manual | Manual (From the date of WO launch) | Manual | SAP | SAP | MASTER TRACKER | MASTER TRACKER | FORMULA | SAP | SAP | Master tracker | Formula |  | SAP STATUS | SAP STATUS | SAP STATUS | SAP STATUS | SAP STATUS | SAP STATUS | SAP STATUS | SAP STATUS | SAP STATUS | SAP STATUS | SAP STATUS | SAP STATUS | SAP STATUS | SAP STATUS | SAP STATUS | SAP STATUS | SAP STATUS | SAP STATUS | SAP STATUS | SAP STATUS | SAP STATUS | SAP STATUS | SAP STATUS | SAP STATUS | SAP STATUS | SAP STATUS | SAP STATUS | SAP STATUS | SAP STATUS | SAP STATUS | SAP STATUS | SAP STATUS
SAP PN# | WO | SAP STATUS | AGEING | PROJECT | ISSUES | QTY | KMDF/ KMFI | ACTION STATUS | WORK CATEGORY | PRIORITY | ISSUE SUMMARY | RESP | DP/CP | ASSY | EDC | WO ACTIVE DAYS | PO Check | Next Operation Cat | Next Operation Desc | CUSTOMER | PROJECT NOMENCLATURE | OPN PENDING | RM STOCK CHECK | RM CODE | PROJECT2 | COMPLETION% | HANDOVER | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32
Z5791303430400 | 21008325 | FINISHED GOODS STORAGE | 532 | ABS | Waiting for approval | 7 | KMFI | OPEN | FG | PART SUBMITTED | FAI Approval | FG | DP | NO | 0 | 581 | YES | FG | FINISHED GOODS STORAGE | ABS | ABS | 2 | OK | #N/A | ABS | 0.90476 | pending | RS-RM-01 | SMROCELL | SM-DB-01 | SM-DB-03 | QA-BI-01 | SMHTCELL | SMHTCELL | HT-CS-02 | SMPBCELL | SM-HP-01 | SM-CS-01 | SMAOCELL | SMAOCELL | QA-CI-01 | QA-HT-01 | ND-FP-01 | ST-CA-02 | QA-ST-01 | PM-PI-01 | QA-FIHERE | RS-FG-01
Z5791303330400 | 21009970 | FINISHED GOODS STORAGE | 440 | ABS |  | 3 | KMFI | Closed | FG | PART SUBMITTED | FAI Approval | FG | DP | YES |  | 493 | YES | FG | FINISHED GOODS STORAGE | ABS | ABS | 1 | OK | #N/A | ABS | 0.95 | Completed | RS-RM-01 | SMROCELL | SM-DB-01 | SM-DB-03 | QA-BI-01 | SMPBCELL | QA-CI-01 | ST-TA-04 | QA-ST-01 | ST-PS-01 | QA-PS-01 | ST-PS-01 | ST-TU-01 | QA-PS-01 | RS-HD-01 | EQUIP-01 | EQ-QA-01 | AS-PM-02 | QA-FI | RS-FG-01HERE
Z5791303730400 | 21012070 | FINISHED GOODS STORAGE | 354 | ABS | Waiting for approval | 2 | KMFI | OPEN | FG | PART SUBMITTED | FAI Approval | FG | DP | NO | 0 | 396 | YES | FG | FINISHED GOODS STORAGE | ABS | ABS | 2 | OK | #N/A | ABS | 0.90476 | Completed | RS-RM-01 | SMROCELL | SM-DB-01 | SM-DB-03 | QA-BI-01 | SMHTCELL | SMHTCELL | HT-CS-02 | SMPBCELL | QA-CI-01 | QA-HT-01 | ST-TA-04 | QA-ST-01 | ST-PS-01 | QA-PS-01 | ST-PS-01 | ST-TU-01 | QA-PS-01 | PM-PI-01 | QA-FIHERE | RS-FG-01
Z5791303530400 | 21011882 | FINISHED GOODS STORAGE | 340 | ABS |  | 2 | KMFI | OPEN | FG | PART SUBMITTED | FAI Approval | FG | DP | YES | 0 | 396 | NO | FG | FINISHED GOODS STORAGE | ABS | ABS | 12 | NOT OK | RA1M7011861601 | ABS | 0.53846 | #N/A | RS-RM-01 | SM-WL-01 | SM-WL-01 | SM-CS-01 | QA-WL-01 | QA-CI-02 | ND-FP-01 | ST-CA-02 | QA-ST-01 | ST-PS-01 | QA-PS-01 | ST-TC-01 | ST-TU-01 | QA-PS-01 | RS-HD-01HERE | EQUIP-01 | AS-SE-01 | AS-SE-01 | EQUIP-01 | EQ-QA-01 | AS-PS-01 | AS-PM-02 | QA-FI | AS-PM-02 | AS-PS-02 | RS-FG-01
Z5791319730300 | 21012799 | FINISHED GOODS STORAGE | 311 | ABS | Waiting for approval | 4 | KMFI | OPEN | FG | PART SUBMITTED | FAI Approval | FG | DP | YES | 0 | 351 | YES | FG | FINISHED GOODS STORAGE | ABS | ABS | 2 | OK | #N/A | ABS | 0.92308 | Completed | RS-RM-01 | SMROCELL | SM-DB-01 | SM-DB-03 | QA-BI-01 | SMPBCELL | QA-CI-01 | ST-MA-01 | QA-ST-01 | ST-TA-04 | QA-ST-01 | ST-PS-01 | ST-UM-01 | ST-TU-01 | QA-PS-01 | RS-HD-01 | EQUIP-01 | AS-CD-01 | EQUIP-01 | EQ-QA-01 | AS-PS-01 | AS-QP-01 | ST-UM-01 | AS-PM-02 | QA-FIHERE | RS-FG-01
Z5791303130400 | 21013435 | FINISHED GOODS STORAGE | 302 | ABS | Waiting for approval | 2 | KMFI | OPEN | FG | PART SUBMITTED | FAI Approval | FG | DP | NO | 0 | 323 | YES | FG | FINISHED GOODS STORAGE | ABS | ABS | 2 | OK | #N/A | ABS | 0.86667 | Completed | RS-RM-01 | SMROCELL | SM-DB-01 | SM-DB-03 | QA-CI-01 | ST-TA-04 | QA-ST-01 | ST-PS-01 | QA-PS-01 | ST-PS-01 | ST-TU-01 | QA-PS-01 | PM-PI-01 | QA-FIHERE | RS-FG-01
Z5391064000000 | 21013552 | FINISHED GOODS STORAGE | 256 | ABS | Waiting for approval | 4 | KMFI | OPEN | FG | PART SUBMITTED | FAI Approval | FG | DP | NO | 0 | 291 | YES | FG | FINISHED GOODS STORAGE | ABS | ABS | 2 | OK | #N/A | ABS | 0.91304 | Completed | RS-RM-01 | SMROCELL | SM-DB-01 | SM-DB-03 | QA-BI-01 | SMHTCELL | SMHTCELL | HT-CS-02 | SMPBCELL | SM-TR-01 | SMPBCELL | QA-CI-01 | QA-HT-01 | ST-TA-04 | QA-ST-01 | ST-PS-01 | QA-PS-01 | ST-PS-01 | ST-TU-01 | QA-PS-01 | PM-PI-01 | QA-FIHERE | RS-FG-01
X5393680130300 | 21013403 | FINISHED GOODS STORAGE | 254 | ABS | Engg Review | 6 | KMFI | OPEN | FG | PART SUBMITTED | FAI Approval | FG | DP | NO | 0 | 297 | NO | FG | FINISHED GOODS STORAGE | ABS | ABS | 2 | NOT OK | RM0010012480005 | ABS | 0.91667 | Completed | RS-RM-01 | SMROCELL | SM-DB-01 | SM-DB-03 | QA-BI-01 | SMHTCELL | SMHTCELL | HT-CS-02 | SMPBCELL | SM-HF-01 | HT-AO-02 | QA-CI-02 | QA-HT-01 | ND-FP-01 | ST-TA-04 | QA-ST-01 | ST-PS-01 | QA-PS-01 | ST-PS-01 | ST-TU-01 | QA-PS-01 | PM-PI-01 | QA-FIHERE | RS-FG-01
Z5391067830000 | 21013505 | FINISHED GOODS STORAGE | 251 | ABS | Parts are with Engg_Abhishek,PO not available mail has sent from Engg to teco the part | 5 | KMFI | OPEN | FG | PART SUBMITTED | FAI Approval | FG | DP | YES | 0 | 294 | NO | FG | FINISHED GOODS STORAGE | ABS | ABS | 14 | NOT OK | RM5060610290029 | ABS | 0.5625 | #N/A | RS-RM-01 | SM-RO-03 | SM-DB-03 | SM-DB-01 | QA-CI-02 | ST-MA-01 | QA-ST-01 | ST-MA-01 | QA-ST-01 | ST-CA-02 | QA-ST-01 | ST-PS-01 | QA-PS-01 | ST-TC-01 | ST-TU-01 | ST-MA-01 | QA-PS-01 | RS-HD-01 | EQUIP-01HERE | AS-CD-02 | AS-SE-01 | AS-SE-01 | EQUIP-01 | EQ-QA-01 | AS-SE-01 | AS-SE-01 | EQ-QA-01 | AS-PM-02 | QA-FI | AS-PM-02 | AS-PS-02 | RS-FG-01
Z5393680130400 | 21014390 | FINISHED GOODS STORAGE | 223 | ABS | Drawing Updating | 8 | KMFI | OPEN | FG | PART SUBMITTED | FAI Approval | FG | CP | NO | 0 | 255 | YES | FG | FINISHED GOODS STORAGE | ABS | ABS | 2 | OK | #N/A | ABS | 0.88235 | pending | RS-RM-01 | SMROCELL | SM-DB-01 | SM-DB-03 | QA-BI-01 | SMPBCELL | QA-CI-01 | ST-CC-01 | QA-ST-01 | ST-PS-01 | QA-PS-01 | ST-PS-01 | ST-TU-01 | QA-PS-01 | PM-PI-01 | QA-FIHERE | RS-SF-01
Z5393680130600 | 21014462 | FINISHED GOODS STORAGE | 218 | ABS | Engg issdue_Wrong hardware loaded | 4 | KMFI | OPEN | FG | PART SUBMITTED | FAI Approval | FG | DP | YES | 0 | 235 | YES | FG | FINISHED GOODS STORAGE | ABS | ABS | 6 | NOT OK | RM5171030650065 | ABS | 0.66667 | pending | RS-RM-01 | SMROCELL | SM-DB-01 | SM-DB-03 | QA-BI-01 | SMPBCELL | QA-CI-01 | ST-TA-04 | QA-ST-01 | ST-PS-01 | ST-TU-01 | QA-PS-01 | RS-SF-01HERE | EQUIP-01 | EQ-QA-01 | AS-PM-02 | QA-FI | RS-FG-01
|  | Issue of raw material | for production | [5 empty] | WORK CATEGORY |  |  | RESP |  | ASSY
[9 empty] | COMP-INSP |  |  | ASSY |  | YES
[9 empty] | COMP |  |  | ASSY-INSP |  | NO
[9 empty] | SST |  |  | Engineering
[9 empty] | O/S |  |  | COMP
[9 empty] | FINSP |  |  | COMP-INSP
[9 empty] | FG |  |  | Program
[9 empty] | ASSY-INSP |  |  | Program
[9 empty] | ASSY |  |  | FG
[9 empty] | RM-STORE |  |  | FINSP
[9 empty] | SST-INSP |  |  | HT-INSP
[9 empty] | HT-INSP |  |  | LOADING
[9 empty] | SFG |  |  | O/S
[9 empty] | WELD-INSP |  |  | Maintenance
[9 empty] | CMM |  |  | PPC
[9 empty] | LOADING |  |  | Production
[9 empty] | INW-INSP |  |  | Program
Quality
RM-STORE
SCM
SFG
SST
SST-INSP
#REF!

## Quality
Manual | Formula - redundant | Formula - redundant | From Programs | From Programs | To Check | From Programs | From Programs | Manual drop down | Manual text | Manual drop down
Date | Month | Week | Customer | Part Number | Type | Work order number | Order Type | Current Status | Remarks | D/C
2024-09-26 | SEPTEMBER | 36 | ATLANTIC | Z5791303430400 |  | 21002672 | FAI | Approved |  | CP
2024-09-25 | SEPTEMBER | 36 | ATLANTIC | Z5791303330400 |  | 21002756 | FAI | Approved |  | CP
2024-09-26 | SEPTEMBER | 36 | ATLANTIC | Z5791303730400 |  | 21014016 | FAI | Approved |  | DP
2024-09-20 | SEPTEMBER | 35 | ATLANTIC | Z5791303530400 |  | 21011803 | FAI | Approved |  | DP
2024-09-24 | SEPTEMBER | 36 | ATLANTIC | Z5791319730300 |  | 21005043 | FAI | Approved |  | DP
2024-09-26 | SEPTEMBER | 36 | ATLANTIC | Z5791303130400 |  | 21003087 | FAI | Approved |  | DP
2024-09-24 | SEPTEMBER | 36 | ATLANTIC | Z5391064000000 |  | 21007077 | FAI | Approved |  | DP
2024-09-25 | SEPTEMBER | 36 | ATLANTIC | X5393680130300 |  | 21009445 | FAI | Waiting for approval |  | DP
2024-09-19 | SEPTEMBER | 35 | ATLANTIC | Z5391067830000 |  | 21003861 | FAI | Approved |  | DP
2024-09-25 | SEPTEMBER | 36 | ATLANTIC | Z5393680130400 |  | 21001863 | FAI | Approved |  | DP
2024-09-25 | SEPTEMBER | 36 | ATLANTIC | Z5393680130600 |  | 21003799 | FAI | Approved |  | DP
[8 empty] | Current Status |  | D/C
[8 empty] | Approved |  | CP
[8 empty] | Waiting For Approval |  | DP
Issues

## Engineering_Dashboard
2026-09-30 |  | ENGINEERING DASH BOARD-ASA (All Waves)
Project & Scope |  | GATE 1 |  | GATE 2 |  | GATE 3 |  | Customer Approvals | [9 empty] | GATE 4 |  |  |  | Gate 5 | [11 empty] | Gate 6 (Launch Clerance) | [8 empty] | GATE 7 |  |  |  |  | Gate 8 |  |  |  |  | Remarks
Project | Scope | TDP Available | TDP Pending | Feasibility Completed | Feasibility Pending | P-BOM Creation completed (RM, HW, Consumables) | P-BOM Creation Pending | SST Approval Completed | SST Approval Pending | LAI Approval Completed | LAI Approval Pending | FPQ Approval Completed | FPQ Approval Pending | Tool Concept Approved | Tool Concept App.Pending | Tool Design Approved | Tool Design App.Pending | Conncurrence completed | Concurrence Pending | TRF Given | TRF Not Given | 3D Model Completed | 3D Model Pending | NCP Completed | NCP Pending | Tool Concept Completed | Tool Concept Pending | Tool Design Completed | Tool Design Pending | Tool Fab. Completed | Tool Fab. Pending | Outsourcing Received | Outsourcing Pending | LC Given | Material Cut | LC Pending | ME WIP | TQ Dep. (Launch) | RM Dep. | BOI Dep. | CP WIP | OUTSOURCE (Dossier) Total Scope | FAI Submitted | FAI Approval Pending | FAI Sumission Pending | TQ Dep. (WIP) | Other Dep. | Production Handover Pending | Production Handover Completed | ≤ 3 Batches | > 3 Batches | Cutover given to ASA
ASA NPI-1.1 | 148 | 146 | 2 | 140 | 8 | 139 | 9 | 148 | 0 | 148 | 0 | 142 | 0 | 136 | 6 | 136 | 6 | 136 | 12 | 136 | 0 | 136 | 6 |  |  | 136 | 6 | 136 | 6 | 136 | 6 |  |  | 131 | 131 | 17 | 11 | 6 | 0 | 0 | 0 | 0 | 130 |  | 18 | 0 |  | 13 | 117 | 68 | 26
ASA W1 | 53 | 53 | 0 | 53 | 0 | 53 | 0 | 53 | 0 | 52 | 1 | 53 | 0 | 53 | 0 | 53 | 0 | 53 | 0 | 53 | 0 | 53 | 0 |  |  | 53 | 0 | 53 | 0 | 51 | 2 |  |  | 53 | 52 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 50 |  | 3 | 2 |  | 0 | 50 | 5 | 38
ASA W2 | 618 | 618 | 0 | 618 | 0 | 618 | 0 | 614 | 4 | 610 | 8 | 618 | 4 | 618 | 0 | 616 | 2 | 618 | 0 | 618 | 0 | 616 | 2 |  |  | 618 | 0 | 617 | 1 | 615 | 3 |  |  | 610 | 610 | 8 | 1 | 3 | 0 | 0 | 0 | 0 | 599 |  | 19 | 0 |  | 8 | 591 | 163 | 294
ASA W3A | 313 | 313 | 0 | 313 | 0 | 313 | 0 | 313 | 0 | 307 | 6 | 311 | 2 | 313 | 0 | 313 | 0 | 313 | 0 | 313 | 0 | 313 | 0 |  |  | 313 | 0 | 313 | 2 | 296 | 17 |  |  | 291 | 288 | 22 | 19 | 0 | 1 | 1 | 1 | 41 | 274 |  | 39 | 3 |  | 36 | 238 | 0 | 0
ASA W3B | 276 | 276 | 0 | 276 | 0 | 276 | 0 | 276 | 0 | 275 | 1 | 274 | 0 | 275 | 0 | 212 | 64 | 276 | 0 | 276 | 0 | 250 | 26 |  |  | 276 | 0 | 261 | 15 | 250 | 48 |  |  | 213 | 202 | 63 | 38 | 14 | 9 | 2 | 0 | 232 | 167 |  | 109 | 2 |  | 60 | 107 | 0 | 0
ASA W3C | 351 | 351 | 0 | 351 | 0 | 351 | 0 | 351 | 0 | 310 | 41 | 321 | 0 | 351 | 0 | 317 | 34 | 351 | 0 | 351 | 0 | 324 | 27 |  |  | 351 | 0 | 317 | 34 | 317 | 34 |  |  | 279 | 273 | 70 | 58 | 8 | 4 | 0 | 0 | 307 | 184 |  | 167 | 15 |  | 179 | 5 | 0 | 0
Total | 1759 | 1757 | 2 | 1751 | 8 | 1750 | 9 | 1755 | 4 | 1702 | 57 | 1719 | 6 | 1746 | 6 | 1647 | 106 | 1747 | 12 | 1747 | 0 | 1692 | 61 | 0 | 0 | 1747 | 6 | 1697 | 58 | 1665 | 110 | 0 | 0 | 1577 | 1556 | 181 | 127 | 32 | 14 | 3 | 1 | 580 | 1404 | 0 | 355 | 22 | 0 | 296 | 1108 | 236 | 358 |  |  | Plan - LC - 3A | Planned LC | Actual LC | Plan-FAI Submission - 3A | Plan FAI Submission-Cum | Actual FAI Submission-Cum
Note on S9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: TQ 253, TQ 64
Note on Y11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Under Validation; Received Some Data
Note on AE11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 42 parts contribute to 64 tools
Note on AG11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 53 parts contribute to 74 tools
Note on Y12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Under Validation; Received Some Data
Note on AG12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 35 tools contribute to 28 parts

## Tooling-Dashboard
|  | DETAILS |  |  | GATE |  |  |  | DESIGN |  |  |  |  | MANUFACTURING
Customer Name | Project | Deliverable Part | Part Numbers | No of Tools Required | C.E Validation | Design Validation | Mfg Validation | Tool Proveout | IN-HOUSE PLAN | IN-HOUSE COMP | OUTSOURCED PLAN | OUTSOURCED COMP | STATUS | IN-HOUSE PLAN | IN-HOUSE COMP | OUTSOURCED PLAN | OUTSOURCED COMP | STATUS
AIRBUS ATLANTIC | ABA BATCH-1 | 5 | 5 | 4 | 4 | 4 | 0 | 0 | 4 | 4 | 0 | 0 | 100% | 0 | 0 | 4 | 4 | 100%
AIRBUS ATLANTIC | ABA BATCH-2 | 37 | 37 | 47 | 47 | 47 | 0 | 0 | 47 | 47 | 0 | 0 | 100% | 0 | 0 | 47 | 45 | 95.74%
AIRBUS ATLANTIC | ABA BATCH-3 | 104 | 103 | 135 | 135 | 135 | 0 | 0 | 84 | 84 | 50 | 50 | 99.26% | 0 | 0 | 135 | 120 | 88.89%
AIRBUS ATLANTIC | ABA BATCH-4 | 38 | 38 | 60 | 51 | 48 | 0 | 0 | 44 | 42 | 15 | 6 | 80% | 0 | 0 | 60 | 32 | 53.33%
AIRBUS ATLANTIC | ABA BATCH-5 | 13 | 13 | 14 | 14 | 12 | 0 | 0 | 13 | 11 | 1 | 1 | 85.71% | 0 | 0 | 14 | 5 | 35.71%
AIRBUS ATLANTIC | ABA BATCH-6 | 50 | 91 | 145 | 133 | 113 | 0 | 0 | 63 | 53 | 79 | 60 | 77.93% | 2 | 2 | 143 | 22 | 16.55%
AIRBUS ATLANTIC | ABA BATCH-7 | 97 | 104 | 123 | 123 | 49 | 0 | 0 | 34 | 16 | 78 | 33 | 39.84% | 0 | 0 | 123 | 0 | 0%
AIRBUS HELICOPTER | AH-125 ASSY | 13 | 12 | 13 | 13 | 4 | 0 | 0 | 4 | 2 | 9 | 2 | 30.77% | 0 | 0 | 4 | 0 | 0%
AIRBUS HELICOPTER | AH-H125 | 1 | 46 | 78 | 53 | 20 | 0 | 0 | 53 | 53 | 25 | 0 | 67.95% | 23 | 22 | 30 | 25 | 60.26%
AIRBUS HELICOPTER | AH-H130 | 1 | 178 | 256 | 33 | 117 | 0 | 0 | 96 | 96 | 162 | 24 | 46.88% | 0 | 0 | 125 | 97 | 37.89%
AIRBUS HELICOPTER | AH-H130 ASSY | 23 | 17 | 23 | 23 | 0 | 5 | 0 | 8 | 2 | 15 | 11 | 56.52% | 0 | 0 | 16 | 5 | 21.74%
AERNNOVA | ANN-A220 SKINs | 6 | 6 | 24 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0%
AERNNOVA | ANN-TED & TESS | 252 | 253 | 272 | 53 | 89 | 24 | 0 | 79 | 49 | 191 | 38 | 31.99% | 0 | 0 | 96 | 33 | 12.13%
AERNNOVA | ANN-Tip Assembly | 58 | 58 | 102 | 37 | 14 | 0 | 0 | 39 | 16 | 26 | 6 | 21.57% | 0 | 0 | 49 | 0 | 0%
AIRBUS AEROSTRUCTURE | ASA Skins | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0%
AIRBUS AEROSTRUCTURE | ASA WAVE - I | 11 | 11 | 27 | 27 | 26 | 22 | 0 | 26 | 26 | 1 | 1 | 100% | 0 | 0 | 27 | 8 | 29.63%
AIRBUS AEROSTRUCTURE | ASA WAVE - II | 102 | 102 | 126 | 126 | 118 | 102 | 0 | 85 | 82 | 41 | 38 | 95.24% | 0 | 0 | 120 | 44 | 34.92%
AIRBUS AEROSTRUCTURE | ASA WAVE-IIIA | 53 | 54 | 64 | 64 | 52 | 38 | 0 | 55 | 53 | 9 | 0 | 82.81% | 0 | 0 | 62 | 7 | 10.94%
AIRBUS AEROSTRUCTURE | ASA WAVE-IIIB | 52 | 52 | 75 | 75 | 59 | 0 | 0 | 0 | 0 | 75 | 62 | 82.67% | 0 | 0 | 62 | 2 | 2.667%
AIRBUS AEROSTRUCTURE | ASA WAVE-IIIC | 30 | 30 | 37 | 37 | 6 | 0 | 0 | 0 | 0 | 37 | 18 | 48.65% | 0 | 0 | 18 | 0 | 0%
Boeing | BGS-4 | 1 | 1 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 0 | 0 | 100% | 0 | 0 | 2 | 0 | 0%
Boeing | CCN 010/011 | 1 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 0 | 0 | 100% | 0 | 0 | 2 | 2 | 100%
AIRBUS AEROSTRUCTURE | Cluster 2.1 | 57 | 57 | 104 | 104 | 0 | 0 | 0 | 40 | 0 | 64 | 0 | 0% | 0 | 0 | 104 | 0 | 0%
Dassault | Dassualt | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0%
IAI | IAI | 1 | 20 | 29 | 29 | 24 | 0 | 0 | 29 | 24 | 0 | 0 | 82.76% | 0 | 0 | 24 | 24 | 82.76%
AIRBUS AEROSTRUCTURE | MDCCL | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0%
SAAB | SAAB B-787 | 1 | 11 | 13 | 13 | 13 | 0 | 0 | 13 | 13 | 0 | 0 | 100% | 0 | 0 | 13 | 5 | 38.46%
Boeing | SOW-11 | 1 | 2 | 2 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0%
Boeing | SOW-12 | 1 | 10 | 12 | 10 | 12 | 0 | 0 | 12 | 12 | 0 | 0 | 100% | 0 | 0 | 12 | 9 | 75%
AIRBUS AEROSTRUCTURE | T2_Sections WAVE-1 | 76 | 76 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0%
AIRBUS AEROSTRUCTURE | T2-Sheetmetal | 50 | 50 | 173 | 17 | 0 | 0 | 0 | 31 | 0 | 142 | 0 | 0% | 0 | 0 | 68 | 0 | 0%
| Grand Total | 1088 | 1392 | 1793 | 1210 | 966 | 191 | 0 | 841 | 689 | 878 | 350 | 57.95% | 25 | 24 | 1292 | 489 | 28.61%
Tool Design Monthly (Plan / Actual ) - InHouse | [15 empty] | Tool Design Monthly (Plan / Actual ) - OutSource
Details |  |  | In-House |  |  |  | 2026 | [8 empty] | Details |  |  | OutSource |  |  |  | 2026
Project | Total Part Numbers | Total No of Tools Required | Planned | Completed | Pending | Backlog | September | October | November | December | [5 empty] | Project | Total Part Numbers | Total No of Tools Required | Planned | Completed | Pending | Backlog | September | October | November | December
ABA BATCH-1 | 5 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | ABA BATCH-1 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ABA BATCH-2 | 37 | 47 | 47 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | ABA BATCH-2 | 37 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ABA BATCH-3 | 103 | 135 | 84 | 84 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | ABA BATCH-3 | 103 | 135 | 50 | 50 | 0 | 0 | 0 | 0 | 0 | 0
ABA BATCH-4 | 38 | 60 | 44 | 42 | 2 | 2 | 0 | 0 | 0 | 0 | [5 empty] | ABA BATCH-4 | 38 | 60 | 15 | 6 | 9 | 7 | 0 | 0 | 0 | 10
ABA BATCH-5 | 13 | 14 | 13 | 11 | 2 | 2 | 0 | 0 | 0 | 0 | [5 empty] | ABA BATCH-5 | 13 | 14 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 2
ABA BATCH-6 | 91 | 145 | 63 | 53 | 10 | 10 | 0 | 0 | 0 | 0 | [5 empty] | ABA BATCH-6 | 91 | 145 | 79 | 60 | 19 | 14 | 0 | 0 | 0 | 30
ABA BATCH-7 | 104 | 123 | 34 | 16 | 18 | 18 | 0 | 0 | 0 | 0 | [5 empty] | ABA BATCH-7 | 104 | 123 | 78 | 33 | 45 | 45 | 0 | 0 | 0 | 74
AH-125 ASSY | 12 | 13 | 4 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | [5 empty] | AH-125 ASSY | 12 | 13 | 9 | 2 | 7 | 5 | 1 | 0 | 0 | 9
AH-H125 | 46 | 78 | 53 | 53 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | AH-H125 | 46 | 78 | 25 | 0 | 25 | 25 | 0 | 0 | 0 | 25
AH-H130 | 178 | 256 | 96 | 96 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | AH-H130 | 178 | 256 | 162 | 24 | 138 | 133 | 0 | 0 | 0 | 135
AH-H130 ASSY | 17 | 23 | 8 | 2 | 6 | 5 | 0 | 1 | 0 | 0 | [5 empty] | AH-H130 ASSY | 17 | 23 | 15 | 11 | 4 | 4 | 0 | 0 | 0 | 10
ANN-A220 SKINs | 6 | 24 | 7 | 0 | 7 | 1 | 0 | 0 | 0 | 6 | [5 empty] | ANN-A220 SKINs | 6 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24
ANN-TED & TESS | 253 | 272 | 79 | 49 | 30 | 29 | 0 | 1 | 0 | 0 | [5 empty] | ANN-TED & TESS | 253 | 272 | 191 | 38 | 153 | 142 | 0 | 0 | 0 | 184
ANN-Tip Assembly | 58 | 102 | 39 | 16 | 23 | 22 | 18 | 1 | 0 | 0 | [5 empty] | ANN-Tip Assembly | 58 | 102 | 26 | 6 | 20 | 17 | 0 | 0 | 0 | 76
ASA Skins | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | ASA Skins | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
ASA WAVE - I | 11 | 27 | 26 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | ASA WAVE - I | 11 | 27 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
ASA WAVE - II | 102 | 126 | 85 | 82 | 3 | 2 | 0 | 0 | 0 | 0 | [5 empty] | ASA WAVE - II | 102 | 126 | 41 | 38 | 3 | 0 | 0 | 0 | 0 | 2
ASA WAVE-IIIA | 54 | 64 | 55 | 53 | 2 | 2 | 0 | 0 | 0 | 0 | [5 empty] | ASA WAVE-IIIA | 54 | 64 | 9 | 0 | 9 | 0 | 0 | 0 | 0 | 2
ASA WAVE-IIIB | 52 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | ASA WAVE-IIIB | 52 | 75 | 75 | 62 | 13 | 12 | 0 | 0 | 0 | 12
ASA WAVE-IIIC | 30 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | ASA WAVE-IIIC | 30 | 37 | 37 | 18 | 19 | 19 | 0 | 0 | 0 | 19
BGS-4 | 1 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | BGS-4 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CCN 010/011 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | CCN 010/011 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cluster 2.1 | 57 | 104 | 40 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | [5 empty] | Cluster 2.1 | 57 | 104 | 64 | 0 | 64 | 3 | 0 | 0 | 0 | 104
Dassualt | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Dassualt | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
IAI | 20 | 29 | 29 | 24 | 5 | 5 | 0 | 0 | 0 | 0 | [5 empty] | IAI | 20 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
MDCCL | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | MDCCL | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
SAAB B-787 | 11 | 13 | 13 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | SAAB B-787 | 11 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SOW-11 | 2 | 2 | 2 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | [5 empty] | SOW-11 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
SOW-12 | 10 | 12 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | SOW-12 | 10 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2_Sections WAVE-1 | 76 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | T2_Sections WAVE-1 | 76 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
T2-Sheetmetal | 50 | 173 | 31 | 0 | 31 | 9 | 4 | 7 | 4 | 11 | [5 empty] | T2-Sheetmetal | 50 | 173 | 142 | 0 | 142 | 73 | 31 | 14 | 2 | 168
Grand Total | 1437 | 1962 | 868 | 685 | 183 | 151 | 22 | 10 | 4 | 17 | [6 empty] | 1442 | 1966 | 1020 | 350 | 670 | 499 | 32 | 14 | 2 | 897
Tool Manufacturing Monthly (Plan / Actual ) - InHouse | [15 empty] | Tool Manufacturing Monthly (Plan / Actual ) - Outsource
Details |  |  | In-House | [12 empty] | Details |  |  | Outsource |  |  |  | 2026
Project | Total Part Numbers | Total No of Tools Required | Planned | Completed | Pending | Backlog | September | October | November | December | [5 empty] | Project | Total Part Numbers | Total No of Tools Required | Planned | Completed | Pending | Backlog | September | October | November | December
ABA BATCH-1 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | ABA BATCH-1 | 5 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0
ABA BATCH-2 | 37 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | ABA BATCH-2 | 37 | 47 | 47 | 45 | 2 | 2 | 0 | 0 | 0 | 0
ABA BATCH-3 | 103 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | ABA BATCH-3 | 103 | 135 | 135 | 120 | 15 | 8 | 0 | 1 | 0 | 0
ABA BATCH-4 | 38 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | ABA BATCH-4 | 38 | 60 | 60 | 32 | 28 | 2 | 21 | 4 | 0 | 0
ABA BATCH-5 | 13 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | ABA BATCH-5 | 13 | 14 | 14 | 5 | 9 | 0 | 0 | 0 | 0 | 0
ABA BATCH-6 | 91 | 145 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | ABA BATCH-6 | 91 | 145 | 143 | 22 | 121 | 1 | 46 | 28 | 30 | 0
ABA BATCH-7 | 104 | 123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | ABA BATCH-7 | 104 | 123 | 123 | 0 | 123 | 0 | 1 | 57 | 0 | 65
AH-125 ASSY | 12 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | AH-125 ASSY | 12 | 13 | 4 | 0 | 4 | 0 | 0 | 2 | 0 | 0
AH-H125 | 46 | 78 | 23 | 22 | 1 | 1 | 0 | 0 | 0 | 1 | [5 empty] | AH-H125 | 46 | 78 | 30 | 25 | 5 | 0 | 5 | 0 | 0 | 0
AH-H130 | 178 | 256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | AH-H130 | 178 | 256 | 125 | 97 | 28 | 13 | 7 | 2 | 4 | 0
AH-H130 ASSY | 17 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | AH-H130 ASSY | 17 | 23 | 16 | 5 | 11 | 1 | 0 | 0 | 1 | 2
ANN-A220 SKINs | 6 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | ANN-A220 SKINs | 6 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ANN-TED & TESS | 253 | 272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | ANN-TED & TESS | 253 | 272 | 96 | 33 | 63 | 12 | 14 | 13 | 0 | 11
ANN-Tip Assembly | 58 | 102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | ANN-Tip Assembly | 58 | 102 | 49 | 0 | 49 | 0 | 0 | 0 | 0 | 0
ASA Skins | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | ASA Skins | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ASA WAVE - I | 11 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | ASA WAVE - I | 11 | 27 | 27 | 8 | 19 | 13 | 0 | 0 | 0 | 0
ASA WAVE - II | 102 | 126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | ASA WAVE - II | 102 | 126 | 120 | 44 | 76 | 40 | 3 | 0 | 0 | 0
ASA WAVE-IIIA | 54 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | ASA WAVE-IIIA | 54 | 64 | 62 | 7 | 55 | 52 | 2 | 1 | 0 | 0
ASA WAVE-IIIB | 52 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | ASA WAVE-IIIB | 52 | 75 | 62 | 2 | 60 | 0 | 46 | 14 | 0 | 0
ASA WAVE-IIIC | 30 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | ASA WAVE-IIIC | 30 | 37 | 18 | 0 | 18 | 0 | 3 | 15 | 0 | 0
BGS-4 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | BGS-4 | 1 | 2 | 2 | 0 | 2 | 0 | 2 | 0 | 0 | 0
CCN 010/011 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | CCN 010/011 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
Cluster 2.1 | 57 | 104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Cluster 2.1 | 57 | 104 | 104 | 0 | 104 | 0 | 0 | 0 | 0 | 4
Dassualt | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | Dassualt | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
IAI | 20 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | IAI | 20 | 29 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0
MDCCL | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | MDCCL | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SAAB B-787 | 11 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | SAAB B-787 | 11 | 13 | 13 | 5 | 8 | 0 | 0 | 0 | 0 | 0
SOW-11 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | SOW-11 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SOW-12 | 10 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | SOW-12 | 10 | 12 | 12 | 9 | 3 | 2 | 0 | 0 | 0 | 0
T2_Sections WAVE-1 | 76 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | T2_Sections WAVE-1 | 76 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T2-Sheetmetal | 50 | 173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | T2-Sheetmetal | 50 | 173 | 68 | 0 | 68 | 0 | 0 | 0 | 0 | 0
Grand Total | 1306 | 1780 | 25 | 24 | 1 | 1 | 0 | 0 | 0 | 1 | [5 empty] | Grand Total | 1442 | 1966 | 1360 | 489 | 871 | 146 | 150 | 137 | 35 | 82