MASPL – BUD

DOCUMENT CONTROL

| DOCUMENT NAME | Business Understanding Document (BUD) |
| --- | --- |
| DOCUMENT NO. | v-1.0.0 |

AUTHORISATION

|  | Prepared By | Reviewed By | Authorised By |
| --- | --- | --- | --- |
| Name | Priyank Jain | Mehul Panchal |  |
| Designation | Team Lead | Project Manager |  |
| Date | 28/9/2026 |  |  |

VERSION HISTORY

| VERSION | DATE | PREPARED BY | CHANGES & REASONS FOR CHANGE |
| --- | --- | --- | --- |
| V-1.0.0 | 28/9/2026 | Priyank Jain | Initial draft |

DISTRIBUTION LIST

| Sr. # | Location | Department |
| --- | --- | --- |

Next Review Date:

Problem statement

MASPL currently tracks launch-to-delivery activities across multiple functions such as Business Development, Program, Engineering, PPC, Tooling, SCM / Procurement, Production, Quality and Stores. The supplied process flow shows that the current process uses SAP, Excel, internal server / ledger and email-based updates across stages. The objective of this application is to provide a single workflow-enabled platform for visibility, accountability, ageing, status tracking, exception management and management reporting.

Executive Summary

MASPL currently manages Project Launch, Tooling, Production WIP, Dependencies, Actions, and Issues using multiple Excel files, SAP transactions, emails, and server folders. This leads to data duplication, lack of visibility, delayed follow-ups, and manual reporting.

The objective of the proposed application is to provide a centralized web-based platform to track the complete lifecycle from Contract Receipt → Engineering → Tooling → Procurement → Production → Quality → FAI Submission.

Business Objectives

Business Goals

- Single source of truth for all projects.

- Replace Excel-based trackers.

- Improve cross-functional collaboration.

- Enable management visibility through dashboards.

- Reduce manual follow-ups via notifications.

- Provide auditability and compliance.

- Enable SAP data imports and future integration.

- Track ownership and accountability across departments.

Scope of Work

In Scope

Core Modules

- User Management, Roles, Masters

- Project Tracker

- Tooling Tracker

- BD Module

- Program Module

- Configuration Module

- Engineering Module

- Tooling Module

- SCM Module

- PPC Module

- Production Module

- Quality Module

- Stores Module

- Production WIP Tracker

- Dependency & Action Tracker

- Dashboard & MIS

- Audit Trail

- SSO Login

- SAP Upload & Data Import

- Logs Maintenance

- Reports Module

- Deployment & Server Setup

- SAP Integration (Daily Sync)

1. User Roles

| Role | Responsibility |
| --- | --- |
| Super Admin | User Management, Masters, Configuration, Workflow Management |
| BD User | Bid creation and customer RFQ inputs, Dashboard, Reports |
| Program User | Project planning and launch schedule, Dashboard, Reports |
| Configuration | Update Work Order, Dashboard, Reports |
| Engineering | Engineering milestones and approvals, Dashboard, Reports |
| Tooling User | Tool design, tool manufacturing, TRS/TRF/TL tracking, Dashboard, Reports |
| SCM User | PR/PO, Vendor, Material Procurement, Dashboard, Reports |
| PPC User | WO planning and production readiness, Dashboard, Reports |
| Production User | Production status updates, Dashboard, Reports |
| Quality User | Inspection & FAI activities, Dashboard, Reports |
| Stores User | RM, BOI, FG, SFG status, Dashboard, Reports |

SSO with MFA login will be enabled for all assign users.

2. End-to-End Workflow

Stage 1 : BD User

Source Sheet: INPUT_BD

Input Methods

- Excel Upload

- Excel Download

- Online Form Entry

Fields

SAP Driven

- Doc Type

- Doc No

- Doc Date

- Version No

- Customer Code

- Bid Valid from Date

- Bid Valid to Date

User Input

- Project Name

- Customer Material Code

- RC Price

- NRC OT Price

- Price Currency

- Planned Submission Date

Auto formula

- NRC Price (Formula Provide by Business)

- NRC Amortized Qty (Formula Provide by Business)

After submitting:

Status = "Pending Program Review"

Data flows to Program module automatically.

Reference: INPUT_BD sheet

Stage 2 : Program

Source Sheet: Programs

Auto Populate

| Program Field | Source |
| --- | --- |
| Project | INPUT_BD.Project_Name |
| Material Number | INPUT_BD.Customer_material_code |
| Planned Submission Date | INPUT_BD.Planned Submission Date |

Auto Calculation

Planned Launch Date = Planned Submission Date - 64 Days

SAP Fields

- Actual Release Date

- Actual Submission Date

Program User Inputs

- Customer

- PART DESCRIPTION

- Sub project name

- Type

- Order Type (FAI / DFAI)

- Annual Demand

- Remarks

After submitting

Status = Pending Engineering

Reference: Programs sheet

Stage 3 : Configuration

Configuration role will insert value from

SAP Fields

- W/O – SAP

- W/O Date - SAP

Configuration User Inputs

- WO PLAN RELEASE DATE

- LAUNCH STATUS - refer from program if actual release date is there states is released (Part is launched)

Stage 4 : Engineering

Source Sheet: Engineering

This module will own all milestones from TDP till Tool Approval.

Reference: Engineering sheet

Auto Populate

- FAI SUBMISSION PLAN DATE - Programs (Planned Submission Date)

- MASPL PN (AS PER SAP) – Program (Material Number)

- CUSTOMER PN – Same as MASPL PN with “-”

- PART DESCRIPTION – Program (PART DESCRIPTION)

- Project – Program (Project)

- Sub project name – Program (Sub project name)

- TYPE – Program (TYPE)

Auto Calculated Dates

- FINAL INSPECTION (Plan date) = FAI SUBMISSION PLAN DATE – 3 Days

- ASSY (Plan date) = FINAL INSPECTION (Plan date) – 10 Days

- SST (Plan Date) = ASSY (Plan date) – 7 Days

- PART CONFIG (Plan date) = SST (Plan Date) – 15 Days

- COMP (Plan date) = PART CONFIG (Plan date) – 7 Days

- ISSUE OF RM (Plan date) = COMP (Plan date) – 15 Days

- FAI LAUNCH STSTUS (WO PLAN RELEASE DATE) = ISSUE OF RM (Plan date) – 4 Days

- NC PROGRAM STATUS (NC PROGRAM COMPLETION PLAN DATE) = FAI LAUNCH STSTUS (WO PLAN RELEASE DATE) – 7 Days

- RAW MATERIAL & BOI (RM NEED DATE) = ISSUE OF RM (Plan date) – 21 Days

- TOOLS (TOOL PLAN DATE) = FAI LAUNCH STSTUS (WO PLAN RELEASE DATE) – 21 Days

- CONCURRENCE (CONCURRENCE PLAN DATE) = FAI LAUNCH STSTUS (WO PLAN RELEASE DATE) – 120 Days

- FEASIBILITY STUDY (FEASIBILITY PLAN DATE) = FAI LAUNCH STSTUS (WO PLAN RELEASE DATE) – 150 Days

- TDP (TDP PLAN DATE) = FAI LAUNCH STSTUS (WO PLAN RELEASE DATE) – 180 Days

Engineering Inputs

- SAFETY CLASS

- PROCESS

- TDP

  - TDP AVAILABILITY (Yes/ No)

  - TDP ACTUAL DATE (TDP available or not if available then only insert date)

- Feasibility

  - FEASIBILITY ACTUAL DATE

  - FEASIBILTY STUDY

- BOM CREATION

  - RM BOM STATUS

  - CONSUMABLE BOM STATUS

  - HW BOM STATUS

- Consumable APPROVAL

  - SST PROCESS QUALIFICATION REQUIREMENTS

  - SST PROCESS NEEDED QULIFICATION

  - SST PROCESS QUALIFICATION STATUS

  - LAI APPROVAL

  - FPQ APPROVAL REQUIREMENTS (Yes/No)

  - FPQ APPROVAL STATUS (APPROVED/ME WIP/CUST.WIP)

  - ME EDC

  - CUST. EDC

- Concurrence

  - CONCURRENCE ACTUAL DATE

  - CONCURRENCE STATUS

- Tool Approval

  - TOOL CONCEPT REQUIREMENTS

  - TOOL CONCEPT APPROVAL STATUS

  - TOOL DESIGN APPROVAL

- RAW MATERIAL & BOI

  - FINAL TEMP

  - THICKNESS

  - RM/BOI Num

  - BOI NEED DATE

  - RM STATUS

  - BOI STATUS

- NC PROGRAM STATUS

  - NC PROGRAM TYPE

  - NC PROGRAM COMPLETION ACTUAL DATE

- FAI LAUNCH STSTUS

  - DELINQUENCY

  - LC DEPENDENCY

  - LC DEPENDENCY BREAKUP

  - DOSSIAR INHOUSE/OUTSOURCE (if inhouse filled by Engineering if outsource then data coming from SCM)

  - PRIORITY

  - TQ REQUIRED

  - TQ RAISED

- Remarks

SAP Fetch

- ISSUE OF RM - ACTUAL DATE

- COMP – ACTUAL DATE

- PART CONFIG (FORMING +HT+M/C) – ACTUAL DATE

- SST – ACTUAL DATE

- ASSY – ACTUAL DATE

- FINAL INSPECTION – (Comp. FI & SST, Comp. FI & LC, ACTUAL DATE, REVIEW)

- FAI SUBMISSION – (FAI SUBMISSION ACTUAL DATE, DELAY, FAI SUBMISSION DEPENDENCY, FAI SUBMISSION DEPENDENCY BREAKUP)

Fetch from Tooling (these all fields fetch only if Tools Needed is yes)

- TOOLS NEEDED? (Formula if this part is available in tooling, then yes otherwise No)

- TOOL TYPE (this value coming from tooling)

- NO OF TOOLS

- COMMITTED DATE

- TOOL ACTUAL DATE

- TOOL AVAILIABILITY

- TRF HANDOVER

- TOOL DESIGN

- TOOL FABRICATION

- TOOL NUMBER

- TL CODE

- DEPENDENCY

Reference: Engineering sheet

After completion

Status = Pending Tooling

Stage 5 : Tooling

Source Sheet: Tooling

Reference: Tooling sheet

Auto Populate

- Customer – Program (Customer)

- Project – Program (Project)

- Derivable Part No – Program (Material Number)

- Part No - Program (Material Number with “- “)

- SAP No -- Formula (business will provide it)

- Annual Demand – Input_BD (Annual Demand)

- Part Launch Date = Program (Planned Launch Date)

Auto Calculated Dates

- Tool Lob Date = Part Launch Date – 21 Days

- Mfg End Date (Plan) = Tool Lob Date – 21 Days

- Mfg Start Date (Plan) = Mfg End Date (Plan) – 90 Days

- TRS Plan Date (Mfg) = Mfg Start Date (Plan) – 7 Days

- Design End Date (Plan) = TRS Plan Date (Mfg) – 15 Days

- Design Start Date (Plan) = Design End Date (Plan) – 60 Days

- TRF Plan Date = Design Start Date (Plan) – 22 Days

Tooling Inputs

- GATE-1

  - C.E Input Data validation (Yes/No)

  - Remarks (C.E)

- TRF Act Date

- TRF No

- Tool Number

- Tool Description (Dropdown – Master)

- Operation

- Complexity (Dropdown – Master)

- Design (Dropdown – Master)

- SCM Design (these will display only if Design is Outsource)

  - TRS Number (Design)

  - TRS Plan Date(Design)  --  Formula

  - TRS Act Date (Design)

  - PR Number (Design)

  - PR Date (Design)

  - PO Date(Design)    ----- From SCM master

  - PO No(Design)   ----- From SCM master

  - Vendor Info (Design) ----- From SCM master

- Design Start Date (Actual)

- Design End Date (Actual)

- CustomerApproval

  - Applicability

  - Cust. Plan Date

  - Cust. Actual Date

- GATE-2

  - MASPL Tool Design Validation (Yes/No)

  - Validation Remarks

- Design Status (Dropdown – Master)

- Delay (Design) – Formula

- Delay Reason (Design) (Dropdown – Master)

- Tool Length

- Tool Width

- Tool Height

- TL CODE (SAP)

- Manufacturing (Outsourced) (Dropdown – Master)

- SCM Maf (these will display only if Design is Outsource)

  - TRS (Mfg)

  - TRS Act Date (Mfg)

  - PR Number (Mfg)

  - PR Date (Mfg)

  - PO Date (Mfg) ----- From SCM master

  - PO No (Mfg) ----- From SCM master

  - Vendor Info (Mfg) ----- From SCM master

- Supplier Commited Date

- Tool Received Date

- Mfg Status (Dropdown – Master)

- Delay (Mfg.)  -- Formula

- Delay Reason (Mfg) (Dropdown – Master)

- MASPL Tooling Quality Acceptance (Yes/NO)

- GATE-3

  - MASPL Tool Buy-Off (Mfg) (Yes/No)

  - Buy-Off Remarks (Mfg)

- GATE-4

  - FAI TOOL PROVEOUT (Yes/No)

  - Proveout Remarks

  - ACCEPTANCE / REJECTION CRITERIA

- Tool Handover to Stores

- TOOL LIFE CYCLE

- Validation Frequency

- Previous Validation Date

- Next Validation Date --- Formula

- Remarks

Key Business Rule

Relationship:

Part Number

|

+--- Tool 1

+--- Tool 2

+--- Tool 3

``

Therefore:

- Parent = Derivable Part Number

- Child = Tool Number

Design Section

- Design Type

  - Inhouse

  - Outsourced

Manufacturing Section

- Manufacturing Type

  - Inhouse

  - Outsourced

Conditional Workflow

Design = Inhouse

SCM not required for Design

Design = Outsourced

SCM approval required

Manufacturing = Inhouse

SCM not required

Manufacturing = Outsourced

SCM involvement mandatory

Status:

Pending SCM

Stage 6 : SCM

Source Sheet: SCM

Reference: SCM sheet

Auto Populate

- Customer Department = Program (Project)

- TRS Number = Tooling (SCM - TRS (Mfg))

- PR Number = Tooling (SCM - PR Number (Mfg))

- TL Code = Tooling (TL CODE (SAP))

- Description = Tooling (Tool Description)

SCM inputs

- Supplier No.

- Current status / Live Status

- First Cut ETA

- Current ETA

- QTY

- Remarks

SAP Data

- Items of requisition

- PR + Data sharing data

- PO. No

- PO Date

Reflection Logic

Data entered in SCM must automatically update corresponding Engineering and Tooling records.

After completion:

Status = Pending PPC

Stage 7 : PPC

Source Sheet: PPC

Reference: PPC sheet

Auto Fetch

- PROJECT

- CUSTOMER

- PROJECT NOMENCLATURE

- PROJECT2

- COMPLETION%  -- Formula

SAP Fetch

- SAP PN#

- WO

- SAP Status

- AGEING

- QTY

- KMDF/ KMFI

- Next Operation Cat

- Next Operation Desc

- RM STOCK CHECK

- RM CODE

- SAP STATUS as per the parts max status is 60 on daily update

PPC Inputs

- ISSUES

- ACTION STATUS  --- (Open/Closed)

- WORK CATEGORY – Master dropdown

- PRIORITY

- ISSUE SUMMARY

- RESP  – Master dropdown

- DP/CP

- ASSY

- EDC

- WO ACTIVE DAYS

- PO Check (Yes/No)

- OPN PENDING  ---- Formula

- HANDOVER

After completion

Note if SAP status = “Issue of raw material” then it is ready to production

Status = Pending Production

Stage 8 : Production

Inputs

- WIP Status

- Issue Summary

- Completion %

- Operation Pending

- Production Remarks

After completion

Status = Pending Quality

Stage 9 : Quality

Inputs

- Date

- Month --- Formula

- Week -- Formula

- Current Status --- Master Dropdown

- Remarks

- D/C – (CP, DP)

Fetch from Program

- Customer

- Part Number

- Work order number

- Order Type

After completion

Status = Pending Stores

Stage 9 : Stores

Inputs

- Only Approval (Yes / No) with remarks any

Final Status

Completed

`

Dashboard Requirements

Engineering Dashboard

Based on Engineering_Dashboard.

KPIs

- Total Projects

- Total Parts

- TDP Pending

- Feasibility Pending

- BOM Pending

- Concurrence Pending

- Tool Approval Pending

- LC Pending

- FAI Pending

- Production Handover Pending

Filters

- Customer

- Project

- Wave

- Month

- Status

Tooling Dashboard

Based on Tooling-Dashboard.

KPIs

- Total Deliverable Parts

- Total Tools

- Inhouse Design %

- Outsource Design %

- Manufacturing Progress %

- Tool Proveout %

- Tool Delay Count

Drill Down

Customer → Project → Part Number → Tool Number

SAP Integration

Daily Scheduled Job

Execution Time : 06:00 AM

Frequency   : Daily

Fetch:

- Material Master

- Project Data

- BOM

- Work Orders

- Production Status

- PR

- PO

- Vendor Status

- Inventory Status

Update application tables.

Audit Trail

Capture for all modules:

Field

Transaction ID

Module

User

Action

Old Value

New Value

Date

Time

IP Address

Example:

User : Engineering_User1

Field : Concurrence Status

Old : Pending

New : Completed

Date : 28-Sep-2026

Time : 11:25 AM

Phase 2 Scope

As mentioned by you:

Notifications

- Email Notifications

- Escalations

- Reminder Engine

- SLA Breach Alerts

RFA Module

- Request For Approval workflow

- Multi-level approvals

- Approval history

APQP Module

- APQP Stage Tracking

- PPAP Documents

- Customer Approval Tracking

- Readiness Dashboard

Recommended Technical Architecture

Front End

- React

Backend

- Phyton

Database

- MySQL

Authentication

- Azure AD SSO (CC service)

Scheduler

- Windows Service / Cron Job

Integration

- SAP RFC / OData / Excel Upload / CC service

Masters Super admin

User master

Role master

Tooling : -

Tool Description

Complexity

Sourcing

Tool Design Status

Design Delay

Manufacturing Status

Manufacturing delay

PPC :-

WORK CATEGORY

RESP

Quality :-

Current Status